## Outage_Schedule
(Transmission lines rated 138kV and higher that limit bulk power transfers are listed)
Nova Scotia Power |  |  |  | For help, contact: |  |  |  |  | FIM (Flow into Metro) |  | Last Update: | Legends
Transmission Operations |  |  |  | nspsoadmin@nspower.ca | [6 empty] | 2024-05-02 14:05 | Please note all Planned Outages in Green indicates new work
Transmission Planned Outage Schedule | [11 empty] | Please note all Planned Outages in Red indicates there was changes from the previous work schedule
MW (Summer/Winter)
Circuit/Element | For Work On | Start Date | Return Date | Reason | CBX | ONI | ONS | EEX@EB | MDRR | FIM | Generation Restrictions | Import/Export | Notes | Work Status
TR5 | TR5 | 2024-03-28 | 2024-06-15 | Maintenance | [7 empty] | Reduce CBX Corridor Limit by 100MW Reduce Mainland at Hastings Corridor Limit by 50MW
NB STOP 24-013 - Lepreau OOS | NB STOP 24-013 - Lepreau OOS | 2024-04-06 | 2024-06-24 | NB Stop | [7 empty] | NB to NS +PEI <=350 - 400MW | NB Load dependent limit
L-6001 | L6001 (132H-127H) | 2024-04-10 07:00 | 2024-05-07 17:00 | Maintenance
L-6545 | 5S-608 | 2024-04-22 11:00 | 2024-05-24 14:00 | Maintenance
NB STOP 24-023 L2131 OOS | NB STOP 24-023 L2131 OOS | 2024-04-25 | 2024-05-02 | NB STOP | [7 empty] | NB to NS +PEI <=300 -350MW | NB Load dependent limit
L-6516 | L6516 (22C-59C) | 2024-04-29 07:00 | 2024-06-27 17:00 | Maintenance | [6 empty] | Generation Restrictions Apply
LIL Bipole Outage | LIL Bipole Outage | 2024-04-30 | 2024-05-03 21:00 | Maintenance
NB STOP - 24-022 - C03-8 OOS | NB STOP - 24-022 - C03-8 OOS | 2024-04-30 | 2024-05-02 | NB STOP | [7 empty] | NB to NS Import <=300MW
LIL Testing | LIL Testing | 2024-05-03 21:00 | 2024-05-03 23:00 | Testing | [7 empty] | NL to NS Import = OMW
NB STOP 24-023 - ME3-3 OOS | NB STOP 24-023 - ME3-3 OOS | 2024-05-06 | 2024-05-08 | NB STOP | [7 empty] | NB to NS Import <=100MW
L-6001 | L6001 (82V-127H) | 2024-05-08 07:00 | 2024-05-08 17:00 | Maintenance
L-6001 | L6001 (1N-82V) | 2024-05-09 07:00 | 2024-05-14 17:00 | Maintenance
LIL Bipole Outage | LIL Bipole Outage | 2024-05-20 | 2024-06-04 | Maintenance
L-6012 | L6012 Outage | 2024-05-20 07:00 | 2024-05-23 17:00 | Maintenance