## OASIS
(Transmission lines rated 138kV and higher that limit bulk power transfers are listed)
Nova Scotia Power |  |  |  | For help, contact: |  |  |  |  | FIM (Flow into Metro) |  | Last Update: | Legend
Transmission Operations |  |  |  | nspsoadmin@nspower.ca | [6 empty] | 2025-12-30 09:21 | Please note all Planned Outages in Green indicates new updates
Transmission Planned Outage Schedule
Circuit/Element | For Work On | Start Date | Return Date | Reason | CBX | ONI | ONS | EEX@EB | MDRR | FIM | Generation Restrictions | Import/Export | Notes | Work Status
NB STOP | NB STOP | 12/3/2025 | TBD | [8 empty] | #VALUE!
SPS Monitor | SPS Monitor MTCE | 12/17/2025 | TBD | Unplanned maintenance | [7 empty] | NB TO NS IMPORTS LIMITED TO 75MW
NEW BRUNSWICK TIE |  | 12/29/2025 | 12/30/2025 1200 | WEATHER | [7 empty] | NB TO NS IMPORTS LIMITED TO 75MW