## OASIS
(Transmission lines rated 138kV and higher that limit bulk power transfers are listed)
Nova Scotia Power |  |  |  | For help, contact: |  |  |  |  | FIM (Flow into Metro) |  | Last Update: | Legend
Transmission Operations |  |  |  | nspsoadmin@nspower.ca | [6 empty] | 2026-04-24 15:00 | Please note all Planned Outages in Green indicates new updates
Transmission Planned Outage Schedule
Circuit/Element | For Work On | Start Date | Return Date | Reason | CBX | ONI | ONS | EEX@EB | MDRR | FIM | Generation Restrictions | Import/Export | Notes | Work Status
91H-T11 | 91H-T11 | 3/24/2026 | 5/29/2026 | [7 empty] | TC2 must run at Basic System Loads >1500 MW
L-6536 | L-6536 | 4/7/2026 2000 | 4/30/2026 1800 | [8 empty] | Exports to NB limited to 150 MW
67N-T82 | 67N-T82 | 4/14/2026 0830 | 4/27/2026 1400 | [7 empty] | ONS limited to 830MW, ONI limited to 960MW, | Imports from NB limited <= 160 MW
101S-T82 and 101S-B82 | 101S-T82 and 101S-B82 | 4/27/2026 0900 | 4/29/2026 1600 | [8 empty] | 10 min Reserve must be carried for full ML flows East End Exports at East Bay(INC PA1) limited to 1080MW Hastings from limited to 550MW