## OASIS
(Transmission lines rated 138kV and higher that limit bulk power transfers are listed)
Nova Scotia Power |  |  |  | For help, contact: |  |  |  |  | FIM (Flow into Metro) |  | Last Update: | Legend
Transmission Operations |  |  |  | nspsoadmin@nspower.ca | [6 empty] | 7/23/2026 1:30:00 PM | Please note all Planned Outages in Green indicates new updates
Transmission Planned Outage Schedule
Circuit/Element | For Work On | Start Date | Return Date | Reason | CBX | ONI | ONS | EEX@EB | MDRR | FIM | Generation Restrictions | Import/Export | Notes | Work Status
91H-T11 | 91H-T11 | 3/24/2026 | 7/28/2026 | [7 empty] | TC2 must run at Basic System Loads >1500 MW
50W-615 | 50W-615 | 6/22/2026 | 7/31/2026 | [7 empty] | Tusket CT is available for generation
L-6539 | L-6539 | 7/20/2026 | 7/28/2026 | [7 empty] | 1 WC must be available Wreck cove Generation limited to 190MW, Lingan (each unit) Generation limited to 160MW
NB STOP 26-040-BL-R1 | NB STOP 007 | 7/20/2026 | 7/25/2026 | [7 empty] | #VALUE!
LIL POLE 2 OUTAGE | LIL POLE 2 OUTAGE | 7/24/2026 5:00:00 AM | 7/24/2026 11:30:00 PM | [9 empty] | If ML > 168 MWs then {10 min Reserve Requirement = Flows on ML} Else if ML <= 168 MWs {10min Reserve Requirement = 168MWs}
2S-T1 | 2S-T1 | 7/22/2026 10:00 | 7/29/2026 14:30 | [7 empty] | One VJ unit is required in sync
L-6001 | L-6001 | 7/27/2026 8:00 AM | 7/31/2026 16:00 | [8 empty] | ONS limited to 660MW
L-7003 | L-7003 | 7/27/2026 | 8/11/2026 | [8 empty] | CBX limited to 780 MW, ONI: 950 MW
L-6020 | L-6020 | 7/30/2026 8:00 AM | 8/16/2026 4:00 PM | [7 empty] | TK4 must be availble for generation